## Project schedule
| HYDROFORCE INDUSTRIES (PTY) LTD |  |  |  |  | Project start: | 2026-01-29
| Project lead: Fadeel Phillips |  |  |  |  | Display week: | 1
| TASK | START DATE | END DATE | DURATION (WEEKS)
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Part 1
| Project Schedule Planning | 2026-01-29 | 2026-02-01 | 3 | 4
| Business & Financial Plan | 2026-02-01 | 2026-02-23 | 22 | 23
| General Assembly Drawing / Exploded View | 2026-02-23 | 2026-02-28 | 5 | 6
| Parts List (BOM) with Make-or-Buy Decision | 2026-02-28 | 2026-03-03 | 3 | 4
| Manufacturing Drawings of All Components | 2026-03-03 | 2026-03-08 | 5 | 6
SUBMISSION 1
Part 2
| Production Routings/ Spread Sheets (x2) / Production Style | 2026-03-09 | 2026-03-29 | 20 | 21
| Assembly Chart / Operation Process Chart | 2026-03-30 | 2026-04-04 | 5 | 6
| Process Charts & Flow Diagrams | 2026-04-04 | 2026-04-09 | 5 | 6
| Material Flow Pattern (at least 2) | 2026-04-09 | 2026-04-14 | 5 | 6
| Evaluation Criteria & Design Evaluation Sheets | 2026-04-15 | 2026-04-21 | 6 | 7
SUBMISSION 2
Part 3
| ACTIVITY RELATIONSHIP CHART / A.R. WORK SHEET / DIAGRAM | 2026-04-25 | 2026-05-09 | 14 | 15
| RECEIVING / STORES / WAREHOUSE / SHIPPING | 2026-05-10 | 2026-05-23 | 13 | 14
| • Data Collection | 2026-05-10 | 2026-05-15 | 5 | 6
| • Size & Layout Planning | 2026-05-23 | 2026-05-27 | 4 | 5
FACILITIES PLANNING:
| • Offices / Maintenance / Toolroom | 2026-05-27 | 2026-05-28 | 1 | 2
| • Cafeteria / Medical Room | 2026-05-27 | 2026-05-28 | 1 | 2
| • Locker Room & Toilets | 2026-05-27 | 2026-05-28 | 1 | 2
OPERATIONS (PRODUCTION):
| • Workplace/Workstation Design | 2026-06-07 | 2026-06-12 | 5 | 6
| • Layouts of Production Lines with Material Flow | 2026-06-13 | 2026-06-17 | 4
| • Time Standards (Modapts) & Line Balancing | 2026-06-18 | 2026-06-22 | 4
| TOTAL SPACE REQUIREMENT SUMMARY SHEET | 2026-06-23 | 2026-06-26 | 3
| LAYOUT CONSTRUCTION - FIRST DRAFT | 2026-06-27 | 2026-07-05 | 8
| • Detailed factory layout with material flow lines | 2026-07-06 | 2026-07-10 | 4
| PART 3 FIRST DRAFT COMPLETION (13 June 2026) | 2026-07-10 | 2026-07-13 | 3
| LAYOUT CONSTRUCTION - FINAL SUBMISSION | 2026-07-14 | 2026-09-26 | 74
SUBMISSION 3
| Part 1 Submission | Milestone | MILESTONE
| Part 2 Submission | Milestone | MILESTONE
| Part 3 First Draft | Milestone | MILESTONE
| Final Project Submission | Milestone | FINAL MILESTONE
Formulas:
END DATE = [START DATE]+3
START DATE = [END DATE, row above]
START DATE = [END DATE, row above]+1